## START HERE
MARGIN CONTROL KIT
A practical project-economics cockpit for small creative and service agencies.
| YOUR 4-STEP WORKFLOW |  | WORKBOOK SETTINGS
| 01 Set your guardrails |  | Base currency | USD
| Choose one currency for the entire workbook. Set your minimum target margin and the small “watch” band above it. |  | Minimum target margin | 35%
| 02 Add project baselines |  | Watch band above floor | 5%
In PROJECTS, enter the contracted fee, planned hours, and blended internal cost per hour for each project.
03 Log real delivery
Record in-scope hours in TIME LOG. Use one row per person, day, or work block; enter the internal cost rate, not the client bill rate.
04 Capture scope creep
Put extra requests in SCOPE LOG before doing the work. Track approval, delivered hours, and amount billed; review every alert on DASHBOARD.
WHAT EACH TAB DOES
| DASHBOARD | Live portfolio snapshot: project health, margin movement, and scope follow-ups.
| PROJECTS | One row per engagement. Yellow cells are inputs; blue cells are calculated.
| TIME LOG | In-scope delivery hours and internal labor cost. Add entries as work happens.
| SCOPE LOG | Additional requests, approvals, delivery, and invoicing. Separate from the contract baseline.
MODEL NOTES — PLEASE READ
• Single-currency workbook: use one code across all projects. Amounts are not converted, and portfolio totals are only meaningful when every project uses that currency.
• Forecast cost = actual labor cost to date + remaining baseline hours × planned internal cost rate. Hours above plan do not create negative remaining cost.
• Forecast margin uses the contracted fee only. Once a signed change order changes the contract value, update the project fee in PROJECTS. The scope register itself is not a revenue ledger.
• The kit tracks labor costs, not overhead, tax, contractor invoices, or cash collection. Treat margin flags as management signals, not accounting or tax advice.
• All example clients, people, projects, and figures are fictional; replace or delete them before real use. Each register includes 200 ready-to-use rows.
DESIGN KEY Yellow = type here Blue = formula Teal = workflow / controls Coral = attention needed
Note on I6: All money fields are currency-neutral numbers. The selected code labels the workbook; it does not convert amounts.
Note on I7: A live project is “At risk” when its forecast margin is below this floor.
Note on I8: Projects within this many percentage points above the floor are marked “Watch”.

## DASHBOARD
AGENCY MARGIN CONTROL
ACTIVE PROJECTS |  |  | PORTFOLIO FORECAST MARGIN |  |  | PROJECTS BELOW FLOOR |  |  | SCOPE FOLLOW-UPS
LIVE PROJECT PULSE
Sort or filter in PROJECTS for the full register. The comparison below mirrors the first 15 project rows.
Project ID | Project | Client | Due date | Contract fee | Plan hrs | Actual hrs | Forecast cost | Plan margin | Forecast margin | Health | Scope flags
Forecasts are labor-only estimates from the baseline. Confirm source hours, cost rates, signed fee changes, and scope billing before acting on a flag.

## PROJECTS
PROJECT ECONOMICS
One row per engagement • Set the baseline once, then let actual delivery update the forecast.
Yellow columns are editable. Blue columns calculate automatically. Filter by Health to spot margin drift.
Project ID | Client | Project / engagement | Status | Start date | Due date | Contract fee | Planned hours | Planned internal cost / hr | Planned labor cost | Planned margin | Forecast labor cost | Forecast margin | Actual hours | Actual labor cost | Margin change | Health | Notes
PR-101 | Northstar Studio | Brand system rollout | Active | 2026-09-01 | 2026-11-14 | 12000 | 160 | 42 | [8 empty] | Sample only — fictional client and figures
PR-102 | Cedar & Loom | E-commerce refresh | Active | 2026-09-15 | 2026-11-07 | 9800 | 120 | 38 | [8 empty] | Sample only — fictional client and figures
PR-103 | Atlas Ember | Analytics dashboard | Active | 2026-10-01 | 2026-11-28 | 15000 | 200 | 50 | [8 empty] | Sample only — fictional client and figures
PR-104 | Harborlight Co. | Campaign creative suite | Complete | 2026-08-15 | 2026-10-15 | 7200 | 80 | 45 | [8 empty] | Sample only — fictional client and figures

## TIME LOG
TIME & COST LOG
Record in-scope delivery only. Internal cost rate is what the agency pays or allocates, not the client billing rate.
Tip: a row per contributor / work block gives the most useful actual-cost signal. Yellow = input; blue = formula.
Entry ID | Date | Project ID | Contributor | Workstream | Work description | Hours | Internal cost rate | Labor cost | Notes
TL-001 | 2026-09-03 | PR-101 | Ari Lane | Strategy | Kickoff and positioning workshop | 24 | 50 |  | Fictional sample
TL-002 | 2026-09-12 | PR-101 | Mina Park | Design | Exploration and visual directions | 38 | 48 |  | Fictional sample
TL-003 | 2026-10-02 | PR-101 | Ari Lane | Design | System refinement and reviews | 48 | 52 |  | Fictional sample
TL-004 | 2026-09-17 | PR-102 | Noah Reed | Development | Storefront architecture and setup | 50 | 55 |  | Fictional sample
TL-005 | 2026-10-09 | PR-102 | Mina Park | Design | Product page and mobile states | 50 | 55 |  | Fictional sample
TL-006 | 2026-10-29 | PR-102 | Noah Reed | Development | Rework after revised content handoff | 20 | 55 |  | Fictional sample
TL-007 | 2026-10-04 | PR-103 | Ari Lane | Discovery | Metrics mapping and data audit | 30 | 48 |  | Fictional sample
TL-008 | 2026-10-20 | PR-103 | Noah Reed | Development | Dashboard prototype and connectors | 40 | 50 |  | Fictional sample
TL-009 | 2026-08-20 | PR-104 | Mina Park | Design | Concept and creative direction | 32 | 48 |  | Fictional sample
TL-010 | 2026-09-11 | PR-104 | Ari Lane | Production | Final assets, handoff, and revisions | 48 | 48 |  | Fictional sample

## SCOPE LOG
OUT-OF-SCOPE REGISTER
Capture change requests before they become free work. Follow approval → delivery → invoice; alerts expose unapproved or unbilled delivered effort.
Scope effort and cost also feed project actuals. Change-order fees do not alter the contract fee automatically—update PROJECTS after approval.
Change ID | Date | Project ID | Request / extra work | Status | Estimated hours | Quoted fee | Approved fee | Hours delivered | Fee billed | Internal cost / hr | Labor cost | Attention
CR-201 | 2026-10-28 | PR-102 | Additional landing-page section requested after scope sign-off | Delivered | 8 | 800 | 0 | 8 | 0 | 55
CR-202 | 2026-10-30 | PR-102 | Extra product-copy migration requested by client | Delivered | 6 | 600 | 600 | 5 | 0 | 55
CR-203 | 2026-10-21 | PR-101 | Optional social template set | Quoted | 12 | 900 | 0 | 0 | 0 | 48

## LOOKUPS (hidden)
Status | Scope Status | Currency code
Planning | Identified | USD
Active | Quoted | EUR
On Hold | Approved | GBP
Complete | In Progress | CAD
| Delivered | AUD
| Invoiced | NZD
| Declined | SGD
HKD
JPY
IDR
INR
CHF
SEK
NOK
DKK
AED
ZAR
MXN
BRL